## Config
Migration Project Dashboard
Enter project names, start dates, and speed. Add team members at right — they populate the Sign-Off dropdown on every project sheet.
Early/On Time | +1d late | +2d | +3d | +4d | +5d | Status Complete gated via red highlights. Completed date is manual (static). Hours = ¦Completed - Target¦ × 24.
Team Members
# | Project Name | Start Date | Speed | Mult | Target End | Days | % Complete | Completed | Avg Drift | Status | Sheet | Name | Role
1 | [6 empty] | 0% | 0 |  |  | Project 1
2 | [6 empty] | 0% | 0 |  |  | Project 2
3 | [6 empty] | 0% | 0 |  |  | Project 3
4 | [6 empty] | 0% | 0 |  |  | Project 4
5 | [6 empty] | 0% | 0 |  |  | Project 5
6 | [6 empty] | 0% | 0 |  |  | Project 6
7 | [6 empty] | 0% | 0 |  |  | Project 7
8 | [6 empty] | 0% | 0 |  |  | Project 8
9 | [6 empty] | 0% | 0 |  |  | Project 9
10 | [6 empty] | 0% | 0 |  |  | Project 10
11 | [6 empty] | 0% | 0 |  |  | Project 11
12 | [6 empty] | 0% | 0 |  |  | Project 12
13 | [6 empty] | 0% | 0 |  |  | Project 13
14 | [6 empty] | 0% | 0 |  |  | Project 14
PORTFOLIO TOTALS | [6 empty] | 0% | 0 |  | 0/0
Portfolio Progress — % Complete by Project

## Project 1
Project 1 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 2
Project 2 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 3
Project 3 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 4
Project 4 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 5
Project 5 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 6
Project 6 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 7
Project 7 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 8
Project 8 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 9
Project 9 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 10
Project 10 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 11
Project 11 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 12
Project 12 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 13
Project 13 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0

## Project 14
Project 14 — Assign name on Config sheet
Start Date: |  | 0 | Speed: | 0 |  | Mult: |  | Target End: |  |  | Days:
# | Phase | ID | Task | What Needs to Happen | Owner | Day | Target Date | Status | % Complete | Signed Off By | Report Link | Completed | Drift | Hrs | JIRA | How We Know Its Done | Rollback | Notes
1 | 1 — Discovery | 1.1 | Pull DNS Records | Export all DNS records for the app domain — A, CNAME, MX, TXT, SRV, the works. Grab zone files from the provider. Document TTLs and anything pointing at a CDN or WAF. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full DNS export in the repo, second set of eyes confirmed it | N/A — just docs | Get TTLs, record types, CDN refs
2 | 1 — Discovery | 1.2 | Pull Current Certs | Document every cert bound in IIS — subject, SANs, issuer, expiry, thumbprint. PowerShell: Get-ChildItem Cert:\LocalMachine\My | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert inventory with thumbprints, SANs, expiry confirmed | N/A — just docs | Flag wildcards, intermediates, shared certs
3 | 1 — Discovery | 1.3 | Export IIS Bindings | Dump all IIS site bindings — IP, port, hostname, cert assignment. Get-WebBinding or appcmd. Both HTTP and HTTPS. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Binding export saved, mapped to DNS records and certs | N/A — just docs | Watch for SNI, IP-specific bindings, weird ports
4 | 1 — Discovery | 1.4 | Map Application Dependencies | Find every reference to the current domain — connection strings, API endpoints, OAuth redirect URIs, CORS policies, webhooks, hardcoded URLs. Check web.config, appsettings.json, registry, env vars, and anything external that calls back. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Dependency matrix done, every old-domain ref catalogued with file path | N/A — just docs | External services with callback URLs are the ones that bite you
5 | 1 — Discovery | 1.5 | Map SSO / IdP Configuration | Document current SSO setup — identity provider, protocol (SAML/OIDC), client IDs, redirect URIs, metadata URLs, token endpoints, claim mappings, and any app registrations tied to the domain. If ADFS, pull the relying party trust config. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config fully documented — IdP settings, redirect URIs, client IDs, claim maps all captured | N/A — just docs | Dont forget logout/post-logout redirect URIs, they always get missed
6 | 1 — Discovery | 1.6 | Confirm Static IPs | Verify the VM and DB IPs are static, not DHCP. Document both. No IP change here. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | ipconfig /all saved, static confirmed for app and DB | N/A — just docs | If DHCP, fix it before anything else
7 | 1 — Discovery | 1.7 | Check Firewall & Network Rules | Audit firewall rules, NSGs, LB configs for anything referencing the FQDN. Make sure nothing breaks with the new domain. | Network Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | All rules reviewed, mitigation plan for any FQDN-dependent rules | N/A — just docs | Some firewalls resolve DNS at rule creation, prefer IP rules
8 | 1 — Discovery | 1.8 | Get New Certs | Request new certs for target domain from the CA. All required SANs included. Validate the chain is complete — root, intermediate, leaf. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX in hand, chain validated via certutil, SANs match | Can revert to old cert | If ACME/Lets Encrypt, test issuance in lower env first
9 | 1 — Discovery | 1.9 | Write Rollback Plan | Step-by-step rollback doc — DNS revert, old cert re-bind, IIS restore, config restore, comms plan. Pre-stage everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Rollback plan reviewed and approved, all artifacts accessible | N/A — this IS the rollback plan | Pre-write the rollback PowerShell scripts
10 | 1 — Discovery | 1.10 | Schedule Maintenance Window | Coordinate the migration window. Notify stakeholders, upstream/downstream system owners. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Calendar invites sent, window approved, everyone acknowledged | N/A | Time zones, business hours, SLA stuff
11 | 2 — Backups | 2.1 | Backup IIS Config | appcmd add backup. Grab applicationHost.config and all web.configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Backup verified via dry-run restore, in the repo | Restore IIS from backup | appcmd add backup 'PreMigration'
12 | 2 — Backups | 2.2 | Export Certs as PFX | Export all relevant certs with private keys as PFX. Store securely, document the passwords separately. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | PFX files verified importable on test system, in the vault | Re-import old certs from PFX | Export-PfxCertificate with a strong password
13 | 2 — Backups | 2.3 | Backup App Config | Copy web.config, appsettings.json, env vars, registry keys. Everything. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config backup diffed against live, stored in repo | Restore configs from backup | Include transform files
14 | 2 — Backups | 2.4 | Backup DNS Records | Export or screenshot DNS records from the provider. Zone file if available. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Zone file saved and readable | Revert DNS from backup | Some providers support zone import for quick rollback
15 | 2 — Backups | 2.5 | Export SSO / IdP Configuration | Export the current IdP app registration, relying party trust, or OIDC client config. Screenshot or export the claim mappings, redirect URIs, and any conditional access policies tied to this app. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO config export saved alongside other backups, verified re-importable | Restore IdP config from export | Azure AD: export app manifest JSON. ADFS: export relying party trust XML
16 | 2 — Backups | 2.6 | VM Snapshot | Hypervisor snapshot of the VM. Verify its valid. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot in hypervisor, revert function confirmed | Revert entire VM to snapshot | Nuclear option — make sure theres disk space
17 | 3 — Cutover | 3.1 | Import New Cert | Import PFX into Local Machine Personal store. Full chain — intermediate + root if needed. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert visible in certlm.msc, chain shows OK | Remove new cert, old binding stays | Import-PfxCertificate -CertStoreLocation Cert:\LocalMachine\My
18 | 3 — Cutover | 3.2 | Verify Cert Chain | Make sure the full chain is trusted. Intermediates and root in the right stores. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | certutil -verify -urlfetch passes clean | Install missing chain certs
19 | 3 — Cutover | 3.3 | Update IIS Bindings | Swap the HTTPS binding to the new cert and new hostname. Same IP, same port. SNI if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Get-WebBinding shows new cert + hostname, netsh confirms | Revert binding from backup 2.1 | Set-WebBinding + netsh http add sslcert
20 | 3 — Cutover | 3.4 | Update App Config | Flip all config files to the new domain — base URLs, CORS origins, OAuth redirects, cookie domains, absolute URLs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Config diff shows only expected changes, findstr confirms no old domain refs | Restore from backup 2.3 | grep/findstr for old domain across everything to verify
21 | 3 — Cutover | 3.5 | Update SSO / IdP Registration | Update the identity provider app registration with new redirect URIs, post-logout URIs, and identifier URIs for the new domain. Update SAML metadata endpoint if applicable. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | IdP shows correct new-domain URIs, metadata endpoint resolves, no old domain refs | Revert IdP config from backup 2.5 | Azure AD: update redirect URIs. ADFS: update relying party trust. Okta: update app integration URIs
22 | 3 — Cutover | 3.6 | Update App SSO Config | Update the applications SSO config to match — client metadata URL, authority/issuer, SAML assertion consumer service URL, OIDC redirect URI in web.config or appsettings. Token validation audience needs to match. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | App SSO config points to correct IdP endpoints with new domain URIs, token audience matches | Restore app config from backup 2.3 | Easy to miss the WS-Federation wtrealm or SAML entityID
23 | 3 — Cutover | 3.7 | Update DNS | Point the new domain at the VMs IP. Short TTL (60-300s) in lower env, or pre-lowered in prod. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | nslookup resolves new domain to correct IP | Revert DNS from backup 2.4 | Prod: lower TTL 24-48hrs ahead (see 5.1)
24 | 3 — Cutover | 3.8 | Restart IIS | iisreset, recycle the app pool. Pick up all changes cleanly. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Site running, app pool started, Event Viewer clean | N/A — non-destructive | Brief downtime during iisreset
25 | 3 — Cutover | 3.9 | Verify DNS Propagation | Check propagation across multiple resolvers. Dont move on until its solid. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Resolves from 3+ external resolvers and 2+ regions | Wait or investigate cached TTL | nslookup 8.8.8.8, 1.1.1.1, whatsmydns.net
26 | 4 — Testing | 4.1 | Run Test Scripts | Execute the full test suite — HTTPS/cert, redirects, auth flow including SSO login + 2FA, CRUD, DB connectivity, APIs, webhooks, email links, perf baseline, security scan. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All scripts executed, results recorded, pass/fail documented per script | Log failures, categorize migration vs pre-existing | Update JIRA and this sheet with results
27 | 4 — Testing | 4.2 | SSO End-to-End Validation | Test the full SSO flow — IdP-initiated and SP-initiated login, token validation, claim mapping, group/role assignment, logout + single logout, session timeout, conditional access. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | SSO works both directions, claims correct, logout cleans sessions, no old domain in any redirect | Check IdP logs for failed assertions or redirect mismatches | Hit IdP login directly AND from the app, both need to work
28 | 4 — Testing | 4.3 | Triage & Fix | Review all failures. Migration-caused vs pre-existing. Fix whats ours, re-run the failed tests. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All migration defects fixed, re-runs pass, pre-existing issues documented | If unfixable, assess rollback | Pull in app team for code-level fixes if needed
29 | 4 — Testing | 4.4 | Update JIRA & This Sheet | Get JIRA current with test results, defect resolutions, evidence. Update Status column here for every task. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | JIRA tickets current, this sheet reflects actual status, evidence attached | N/A — just docs | Screenshots, logs, test exports attached to tickets
30 | 4 — Testing | 4.5 | Sign-Off | Collect results. Get formal sign-off from QA, app owner, stakeholders. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Written sign-off, all critical/high defects resolved, accepted risks documented | Dont proceed, fix outstanding issues
31 | 5 — Pre-Prod Prep | 5.1 | Lower Prod DNS TTL (24-48hrs Early) | Drop TTL on the existing prod DNS record to 60-300s. At least 24-48hrs before the migration window. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows reduced TTL, waited 2x old TTL | Raise TTL back | This MUST happen in advance, not day-of
32 | 5 — Pre-Prod Prep | 5.2 | Confirm Window Is Active | Verify the maintenance window is live. Final notification to stakeholders. On-call confirmed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Notification sent, status page updated, on-call team confirmed | Cancel window, send all-clear
33 | 5 — Pre-Prod Prep | 5.3 | Prod VM Snapshot | Snapshot immediately before touching anything. | Infra Admin | #VALUE! | #VALUE! |  | 0% | [6 empty] | Snapshot verified in hypervisor | Revert to snapshot | Check disk space first
34 | 5 — Pre-Prod Prep | 5.4 | Backup Prod IIS, Certs, SSO & Config | Repeat Phase 2 backup steps on production. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All backups created, verified, labelled with timestamp | Restore from these backups
35 | 6 — Prod Cutover | 6.1 | Execute Phase 3 on Production | Run steps 3.1 through 3.9 on the prod VM. Exact same procedures validated in testing. No freelancing. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Cert, bindings, app config, SSO config, DNS all updated, IIS restarted, propagation confirmed | Revert per rollback plan 1.9 | Follow the validated playbook exactly
36 | 7 — Prod Smoke | 7.1 | Run Smoke Scripts on Prod | Smoke test subset against prod — HTTPS, redirects, SSO login (IdP and SP initiated), critical reads, critical writes, top APIs, external integrations, monitoring. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All smoke scripts pass, results in JIRA and this sheet | Log failures, assess rollback severity | External network, multiple browsers, at least one mobile
37 | 7 — Prod Smoke | 7.2 | Smoke Defect Triage | Review failures. Fix immediately or pull the trigger on rollback. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | All failures triaged, fixes applied or rollback initiated | Execute rollback plan 1.9 | Everyone on the call for this
38 | 7 — Prod Smoke | 7.3 | Go / No-Go | Formal decision — keep it live or roll back. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Decision documented, stakeholders signed off | Full rollback if no-go
39 | 8 — Hardening | 8.1 | Raise DNS TTL | Restore TTL to production normal (3600-86400s). | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | dig shows production TTL | Lower again if issues pop up | Wait 2-4hrs stable first
40 | 8 — Hardening | 8.2 | Old Domain Redirect | If old domain stays alive temporarily, set up 301 to new domain. Set an expiration date. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain 301s to new domain for all paths | Remove redirect if causing issues | Plan the sunset date
41 | 8 — Hardening | 8.3 | Update External Refs | Update everything pointing at the old domain — search consoles, socials, partner configs, docs, email signatures, IdP metadata URLs if published externally. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Tracking sheet complete, all external refs updated | N/A — informational | Can take days/weeks, prioritize technical integrations first
42 | 8 — Hardening | 8.4 | Decommission Old SSO Entries | After stabilization, remove or disable the old domain app registration / relying party trust from the IdP. Dont leave stale SSO configs. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old domain SSO entries disabled/removed, no impact to live app | Re-enable old IdP config if needed | Wait until confident before killing the old one
43 | 8 — Hardening | 8.5 | Full Regression on Prod (24-48hrs Out) | After 24-48hrs stable, run the full suite. Catch anything the smoke test missed — scheduled tasks, batch jobs, overnight processes. | QA Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Full regression passes, comparable to pre-migration baseline | Log defects, assess if migration-related | This catches the stuff that only runs at 2am
44 | 8 — Hardening | 8.6 | Remove Old Cert & Snapshot | After stabilization (7-30 days), pull the old cert from the store and delete the VM snapshot. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Old cert gone, snapshot gone, app still running fine | Re-import old cert from PFX | Snapshots degrade VM perf, dont keep them forever
45 | 8 — Hardening | 8.7 | Write Completion Report | Migration report — what changed, test results, issues hit, resolutions, final config state, lessons learned. | Migration Lead | #VALUE! | #VALUE! |  | 0% | [6 empty] | Report distributed, in the repo | N/A — just docs | Include old-to-new mapping for future reference
46 | 8 — Hardening | 8.8 | Close It Out | Final notification to stakeholders. Status page updated. Change ticket closed. | PM | #VALUE! | #VALUE! |  | 0% | [6 empty] | Everyone notified, ticket closed | N/A | Note any in-progress items like external ref updates
TOTALS | [7 empty] | Overall: | 0% |  | Completed: | 0 |  | 0
Avg Drift:
[12 empty] | Max Drift: | 0